## Header
Issued by H.Lagneau
Project EC 6072
Project Manager: Nick SANTOS OLIVERA
Client: VA-KO
Reference: EC_6072_0020
Design Examination of Running Gear Y25Lsd-K Following STI-WAG 2020
NoBo Mission
List of versions:
| Version | Date | Changes
| 1 | 2021-11-09 | Creation
| 2 | 2022-11-07 | Assessment
Document CONFIDENTIEL

## Y25Lsd-K
|  |  | VAKO (Evidences of conformity) |  | CERTIFER (Assessment)
COMMISSION REGULATION (EU) No 321/2013 Consolidated 2020 | Requirement/Information | Applicable to IC | Comments/Values/etc. | Documents | Assessor | Assessment | Remarks | Date | Open/Closed
4.2.3.5.2. Running dynamic behaviour | title | title | title | title | title | title | title | title | title
▼M1 Running dynamic behaviour is permitted to be assessed at interoperability constituent level in accordance with point 6.1.2.1. In this case a specific test or simulation at subsystem level is not required. | Requirement | Running Gear |  | 204 | HL | COMPLIANT | - | 2022-11-07 | C
▼B 4.2.3.6. Running gear | title | title | title | title | title | title | title | title | title
The running gear guarantees to carry and guide the unit safely as well as to transmit braking forces where so required. | Information | -
4.2.3.6.1. Structural design of bogie frame | title | title | title | title | title | title | title | title | title
The integrity of the structure of a bogie frame, all attached equipment and body to bogie connection shall be demonstrated based on methods as set out in point 6.2 of EN 13749:2011. | Requirement | Running Gear |  | 312 311 310 309 | HL | COMPLIANT | - | 2022-11-07 | C
▼M1 The integrity of the structure of a bogie frame is permitted to be assessed at interoperability constituent level in accordance with point 6.1.2.1. In this case a specific test or simulation at subsystem level is not required. | Requirement | Running Gear |  | 312 311 310 309 | HL | COMPLIANT | - | 2022-11-07 | C
5. INTEROPERABILITY CONSTITUENTS | title | title | title | title | title | title | title | title | title
5.1. General | title | title | title | title | title | title | title | title | title
Interoperability constituents (ICs), as defined in Article 2(f) of ►M3 Directive (EU) 2016/797 ◄ , are listed in Section 5.3 together with: | Information | Applicable to CI
— their area of use covering parameters of the subsystem, and | Information | Applicable to CI
— the reference to corresponding requirements defined in Section 4.2. | Information | Applicable to CI
When a requirement is identified in Section 5.3 as being assessed at IC level, an assessment for the same requirement at subsystem level is not required. | Information | Applicable to CI
▼M2 5.2. Innovative solutions | title | title | title | title | title | title | title | title | title
As stated in Article 10a, innovative solutions may require new specifications and/or new assessment methods. Such specifications and assessment methods shall be developed using the process described in point 6.1.3 whenever an innovative solution is envisaged for an interoperability constituent. | Information | Applicable to CI |  |  | HL | NA | - | 2022-11-07 | C
▼B 5.3. Interoperability constituent specifications | title | title | title | title | title | title | title | title | title
5.3.1. Running gear | title | title | title | title | title | title | title | title | title
▼M3 The running gear shall be designed for all application ranges, the areas of use, as defined by the following parameters: | Requirement | Running Gear
—Track gauge | Requirement | Running Gear | 1435 mm | 102 104 | HL | NOTED | - | 2022-11-07 | C
▼B — Maximum speed | Requirement | Running Gear | 100 km/h (Loaded) 120 km/h (Empty) | 201 | HL | NOTED | - | 2022-11-07 | C
—Maximum cant deficiency | Requirement | Running Gear | 130 mm | 201 | HL | NOTED | - | 2022-11-07 | C
— Minimum tare of the unit | Requirement | Running Gear | 16 t | 201 202 | HL | NOTED | - | 2022-11-07 | C
— Maximum axle load | Requirement | Running Gear | 22.5 t | 201 | HL | NOTED | - | 2022-11-07 | C
— Range of distances between bogie pivots or range of wheelbase of ‘two-axle units’ | Requirement | Running Gear | min. 6,5 m max. 20,0 m | 103 201 | HL | NOTED | - | 2022-11-07 | C
— Maximum height of centre of gravity of empty unit | Requirement | Running Gear | 860 mm | 201 | HL | NOTED | - | 2022-11-07 | C
— Coefficient of height of centre of gravity of loaded unit | Requirement | Running Gear | 145.3 | 201 | HL | NOTED | - | 2022-11-07 | C
— Minimum torsional stiffness coefficient of car body | Requirement | Running Gear | 0.5 1010 kNmm2/rad | 201 | HL | NOTED | - | 2022-11-07 | C
— Maximum mass distribution coefficient for empty units with: Where: Izz = moment of inertia of the car body relative to the vertical axis through the centre of gravity of the car body m = mass of the car body 2a* = wheelbase | Requirement | Running Gear | 0.55 | 201 | HL | NOTED | - | 2022-11-07 | C
— Minimum nominal wheel diameter | Requirement | Running Gear | Ø840 mm | 201 | HL | NOTED | - | 2022-11-07 | C
— Rail inclination. | Requirement | Running Gear | 1:20, 1:30 and 1:40 | 201 | HL | NOTED | - | 2022-11-07 | C
The parameters speed and axle load may be considered in combination in order to define the appropriate area of use (e.g. maximum speed and tare weight). | Information | Running Gear | 22,5 t/axle: 100 km/h 20 t/axle: 120 km/h | 205 201 | HL | NOTED | - | 2022-11-07 | C
The running gear shall comply with the requirements expressed in points 4.2.3.5.2 and 4.2.3.6.1. These requirements shall be assessed at IC level. | Requirement | Running Gear |  | 310 204 | HL | COMPLIANT | - | 2022-11-07 | C
6.1.1. Modules | title | title | title | title | title | title | title | title | title
The conformity assessment of an interoperability constituent shall be performed in accordance with the module(s) described in Table 8. | Requirement | Applicable to CI |  | CH1 | HL | COMPLIANT | - | 2022-11-07 | C
▼B These modules are specified in detail in Decision 2010/713/EU. | Requirement | Applicable to CI
6.1.2. Conformity assessment procedures | title | title | title | title | title | title | title | title | title
The manufacturer or his authorised representative established within the Union shall choose one of the modules or module combinations indicated in Table 9 in accordance with the required constituent. | Requirement | Applicable to CI |  | CH1 | HL | COMPLIANT | - | 2022-11-07 | C
▼B Within the application of the chosen module or module combination the interoperability constituent shall be assessed against the requirements mentioned in Section 4.2. If necessary, additional requirements concerning the assessment of particular interoperability constituents are given in the following clauses. | Requirement | Applicable to CI |  | 5.3.1 | HL | COMPLIANT | - | 2022-11-07 | C
▼M3 In case of a specific case applicable to a component defined as interoperability constituent in section 5.3 of this TSI, the corresponding requirement can be part of the verification at interoperability constituent level only in the case where the component remains compliant to the chapters 4 and 5 of this TSI and where the specific case does not refer to a national rule (i.e. additional requirement compatible with the core TSI and fully specified in the TSI). | Information | Applicable to CI |  |  | HL | NA | - | 2022-11-07 | C
In other cases, the verification shall be made at subsystem level; when a national rule applies to a component, the concerned Member State may define relevant applicable conformity assessment procedures. | Information | Applicable to CI |  |  | HL | NA | - | 2022-11-07 | C
6.1.2.1. Running gear | title | title | title | title | title | title | title | title | title
The demonstration of conformity for running dynamic behaviour is set out in EN 16235:2013. | Requirement | Running Gear |  | 310 204 | HL | COMPLIANT | - | 2022-11-07 | C
Units equipped with an established running gear as described in chapter 6 of EN 16235:2013 are presumed to be in conformity with the relevant requirement provided that the running gears are operated within their established area of use. | Requirement | Running Gear |  | 203 204 | HL | COMPLIANT | - | 2022-11-07 | C
The assessment of the bogie frame strength shall be based on clause 6.2 of EN 13749:2011. | Requirement | Running Gear |  | 312 311 310 309 | HL | COMPLIANT | - | 2022-11-07 | C
6.1.3. Innovative solutions | title | title | title | title | title | title | title | title | title
If an innovative solution referred to in Article 10a is proposed for an interoperability constituent, the manufacturer or his authorised representative established within the Union shall apply the procedure set out in Article 10a. | Information | Applicable to CI |  |  | HL | NA | - | 2022-11-07 | C

## Table 8
Modules for conformity assessment of interoperability constituents
Module CA1 | Internal production control plus product verification by individual examination
Module CA2 | Internal production control plus product verification at random intervals
Module CB | EC-Type examination
Module CD | Conformity to type based on quality management system of the production process
Module CF | Conformity to type based on product verification
Module CH | Conformity based on full quality management system
Module CH1 | Conformity based on full quality management system plus design examination
▼M2
Module CV | Type validation by in-service experience (suitability for use)

## Table 9
▼M2
Modules to be applied for interoperability constituents
Point | Constituent | Modules
|  | CA1 or CA2 | CB + CD | CB + CF | CH | CH1 | CV
4.2.3.6.1 | Running gear |  | X | X |  | X
| Running gear — established | X |  |  | X
4.2.3.6.2 | Wheelset | X (*1) | X | X | X (*1) | X
4.2.3.6.3 | Wheel | X (*1) | X | X | X (*1) | X
4.2.3.6.4 | Axle | X (*1) | X | X | X (*1) | X
▼M3
4.2.3.6.6 | Automatic variable gauge system | X (*1) | X | X | X (*1) | X | X (*2)
▼M2
4.2.4.3.5 | Friction element for wheel tread brakes | X (*1) | X | X | X (*1) | X | X (*2)
5.3.5 | Rear-end signal | X |  |  | X
(*1) Modules CA1, CA2 or CH may be used only in the case of products placed on the market, and therefore developed, before the entry into force of this TSI, provided that the manufacturer demonstrates to the NoBo that design review and type examination were performed for previous applications under comparable conditions, and are in conformity with the requirements of this TSI; this demonstration shall be documented, and is considered as providing the same level of proof as module CB or design examination according to module CH1.
(*2) Module CV shall be used in case the manufacturer of friction element for wheel tread brakes has no sufficient return of experience (according to its own judgment) for the proposed design.

## Documents
Document Reference | Full Title | Remark/Comment/etc.
101 Maximum Height of Center of Gravity of Empty Unit | Maximum Height of Center of Gravity of Empty Unit (VK-B.05.01.03) | Center of gravity of the bogie was calculated for Y25Lsd-K .
102 Track gauge | Track Gauge VK-B.05.01.01
103 Wheelbase | Wheelbase VK-B.01.01.02
104 VK-B.05.00.00.00 Klasik Frenli H Tipi Boji (Komple) | Klasik Frenli H Tipi Boji (Komple) VK-B.05.00.00.00 | Project complete technical drawing changed
201 Y25 Bogie without front and rear beams equipped with Compact Brake System; Y25Lsdi(f)-KC1 | Interoperability Constituent Running gear of Subsystem Rolling Stock Y25 Bogie without front and rear beams equipped with Classic Brake System; Y25Lsd-K Overview of main characteristics | Only the tare of the bogie and traffic regime of the bogie are changed.
202 Minimum tare of the bogie | MINIMUM TARE OF THE BOGIE | Only the tare of the bogie and traffic regime of the bogie are changed.
203 Range of distances between bogie pivots or range of wheelbase of 'two-axle units' | Range of distances between bogie pivots or range of wheelbase of ‘two-axle units’
204 Y25 Bogie without front and rear beams equipped with Compact Brake System and Disc Brake System. Running Dynamic Behaviour | Y25 Bogie without front and rear beams equipped with Classical Brake System (Y25Lsd-K), Compact Brake System (Y25Lsdi(f)-KC1) and Disc Brake System (Y25Lss-D). | Moment of Inertia of the bogie was calculated for Y25Lsd-K .
204_1 Moment of Inertia 4392,65 kgxm2 | Moment of Inertia 4392,65 kgxm2
205 Operational and design limitations for bogies of Y25-family | 205 Operational and design limitations for bogies of Y25-family
206 VK-B.05.07.00.00.00 Bogie Brake Sports (Complete) | Bogie Brake Sports (Complete) VK-B.05.07.00.00.00 | Technical drawings of the different components shown.
207 VK-B.05.09.00.00.00 Bogie Rigging (Complete) | Brake Rigging (Complete) VK-B.05.09.00.00.00 | Technical drawings of the different components shown.
309 H_TypeBogie_Structural_Analysis | VAKO H TYPE BOGIE ANALYSIS REPORT
310 Static and Fatigue Test Report | Bogie Frame of the Y25 Bogie {H Frame) of the Producer Va-Ko, Turkey Static and Fatigue Strength Tests
311 H_Type_Bogie_Compare_Report | VAKO H TYPE BOGIE COMPARE ANALYSIS REPORT
312 H _Type_Bogie_Compare_Report | Interoperability Constituent Running gear of Subsystem Rolling Stock Y25 Bogie without front and rear beams equipped with Compact Brake System; Y25Lsdi(f)-KC1 Y25 Bogie without front and rear beams equipped with Classical Brake System; Y25Lsd-K Common use design and FEM analysis